## - User Profile Customization"
Backlog Items | Description | Acceptance Criteria | Story Points | Sprint | Priority
User Story 1: Upload Profile Picture | As a user, I want to upload a profile picture so that I can personalize my profile. | Users can upload a picture from their device. The picture is displayed on the user's profile. The picture can be replaced or removed. | 5 | Sprint 1 | 1
User Story 4: View Profile | As a user, I want to view my profile so that I can see my profile picture, status message, and personal information. | Users can see their profile picture, status message, and updated personal information. | 2 | Sprint 1 | 2
User Story 2: Set Status Message | As a user, I want to set a status message so that I can share my current mood or status with my friends. | Users can input and update a text-based status message. The status message is displayed on the user's profile. | 3 | Sprint 2 | 3
User Story 3: Update Personal Information | As a user, I want to update my personal information (e.g., name, email, phone number) so that my profile is always up-to-date. | Users can update their name, email, and phone number. Changes are saved and reflected on the user's profile. | 5 | Sprint 2 | 4
User Story 5: Privacy Settings | As a user, I want to set privacy settings for my profile information so that I can control who sees my details. | Users can choose who can see their profile picture, status message, and personal information. Settings can be updated and saved. | 8 | Sprint 3 | 5

## Milestones and Timeline
Milestone | Estimated Completion
Basic profile view and picture upload functionality (End of Sprint 1) | Week 2
Full profile customization with status message and updated information (End of Sprint 2) | Week 4
Enhanced privacy controls and final user testing (End of Sprint 3) | Week 6

## Team Roles and Responsibilities
Role | Responsibility
Product Owner | Defines and prioritizes user stories, ensures alignment with project vision.
Scrum Master | Facilitates sprint planning, daily stand-ups, and retrospectives; removes obstacles.
Development Team | Implements user stories, conducts unit testing, ensures feature completeness.

## Risks and Mitigations
Risk | Mitigation
Delays in backend integration for profile updates | Allocate buffer time in each sprint for integration testing.
User privacy concerns | Conduct thorough security and privacy testing, include user feedback.